## Maintenance Plan
Phase | Task Name | Dependency | Duration (hh:mm) | Owner | Notes | Task Start Date | Task End Time | Dep Start Time | Dep End Time | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39
Preparation | Inform the users | Inform the users | 0.125 | Alice |  | 2020-10-01 09:00 | 44105.5 | N/A | N/A | bar: 9 to 12
| Install new servers | Install new servers | 0.16667 | Bob |  | 2020-10-01 09:00 | 44105.5417 | 44105.375 | 44105.5417
| Install OS | Install new servers | 0.020833 | Alice |  | 44105.5417 | 44105.5625 | 44105.375 | 44105.5417 | bar: 13
| Cabeling | Install OS | 0.041667 | Bob |  | 44105.5625 | 44105.6042 | 44105.5417 | 44105.5625 | bar: 13 to 14
| Run fio, cpuburn, stream | Cabeling | 0.041667 | Clara |  | 44105.6042 | 44105.6458 | 44105.5625 | 44105.6042 | bar: 14 to 15
| Select a canary client node | Run fio, cpuburn, stream | 0.0069444 | Alice |  | 44105.6458 | 44105.6528 | 44105.6042 | 44105.6458 | bar: 15
Lustre upgrade test | Install lustre packages | Run fio, cpuburn, stream | 0.020833 | Alice |  | 2020-11-01 09:00 | 44136.3958 | 44105.6042 | 44105.6458 | bar: 9
| Format MDTs | Install lustre packages | 0.020833 | Bob |  | 44136.3958 | 44136.4167 | 44136.375 | 44136.3958 | bar: 9 to 10
| Format OSTs | Install lustre packages | 0.020833 | Bob |  | 44136.3958 | 44136.4167 | 44136.375 | 44136.3958 | bar: 9 to 10
| Set up HA | Install lustre packages | 0.041667 | Bob |  | 44136.3958 | 44136.4375 | 44136.375 | 44136.3958 | bar: 9 to 10
| Mount on a canary node | Set up HA | 0.020833 | Alice |  | 44136.4375 | 44136.4583 | 44136.3958 | 44136.4375 | bar: 10 to 11
| Run canary fio | Mount on a canary node | 0.041667 | Clara |  | 44136.4583 | 44136.5 | 44136.4375 | 44136.4583 | bar: 11 to 12
Lustre upgrade | Announce the maintenance |  | 0.041667 | Alice |  | 2020-12-01 09:00 | 44166.4167 | 44166.375 | 44166.4167 | bar: 9 to 10
| Close cluster | Announce the maintenance | 0.020833 | Alice | Use reservation | 44166.4167 | 44166.4375 | 44166.375 | 44166.4167 | bar: 10
| Kill users’ sessions | Close cluster | 0.0069444 | Alice |  | 44166.4375 | 44166.4444 | 44166.4167 | 44166.4375 | bar: 10
| Install lustre packages on clients | Kill users’ sessions | 0.083333 | Bob |  | 44166.4444 | 44166.5278 | 44166.4375 | 44166.4444 | bar: 10 to 12
| Change fstab, mount lustre | Install lustre packages on clients | 0.020833 | Bob |  | 44166.5278 | 44166.5486 | 44166.4444 | 44166.5278 | bar: 12 to 13
| Run fio | Change fstab, mount lustre | 0.16667 | Clara |  | 44166.5486 | 44166.7153 | 44166.5278 | 44166.5486 | bar: 13 to 17
| Open cluster | Run fio | 0.0069444 | Alice |  | 44166.7153 | 44166.7222 | 44166.5486 | 44166.7153 | bar: 17
| Announce the maintenance end | Open cluster | 0.0069444 | Alice |  | 44166.7222 | 44166.7292 | 44166.7153 | 44166.7222 | bar: 17
|  | HOWTO setup this column: |  |  |  | Put EXACT time to override calculated (for activity start) |  |  |  | 9: Gantt diagram: just check the formula, feel free to fine tune. Color: select cells, Menu→Format→Conditional format→Manage
1. select cells | bar: 9 to 23
2. right click | bar: 9 to 23
3. Data validation | bar: 9 to 23
4. Select range B2:Bn | bar: 9 to 23
To add new row, select any existing row, copy, insert new empty row and paste | bar: 9 to 23
Check Notes tab, it might be more useful than “Notes” column… | bar: 9 to 23
Don’t use duplicates in “Task name” column, it leads to errors. | bar: 9 to 23
Note on G2: Edit this date manually to have all other task start and end dates recalculate in a "cascading" fashion.
Note on G3: Edit this date manually to have all other task start and end dates recalculate in a "cascading" fashion.

## Notes
Reservation Name: | maint-lustre-update-2020-01
Path to FIO: | /opt/benchmarks/fio